## Overview
Grounded PPE Safety Copilot — CV + Vision-Language Model Project Plan
A portfolio research project combining visual detection, spatial reasoning, and multimodal language models
THE GOAL
What you'll build | A grounded PPE safety assistant: it detects people, hardhats, and safety vests; associates equipment with each person; then uses a vision-language model to produce evidence-linked compliance JSON, explanations, and uncertainty warnings in a Gradio demo.
Research question | Under Google Colab constraints, does a hybrid system (open-vocabulary detector + explicit person–PPE rules + VLM) reduce false-safe decisions and unsupported claims compared with detector-only and VLM-only baselines?
Estimated timeline | 7–9 weeks, part-time (~6–10 hrs/week). A 6-week MVP is acceptable; model comparisons and fine-tuning are stretch goals.
THE GOLDEN RULES
1. Keep the completed baseline | Do not restart. Preserve the finished YOLO-World work as the detector-only baseline and build the VLM and hybrid stages on top of it.
2. Ground every conclusion | A safety conclusion must cite visible evidence: detection IDs, boxes or masks, person–PPE relationships, and an uncertainty state. The VLM must not invent evidence.
3. Measure safety risk, not only mAP | Report detection quality, person-level compliance F1, false-safe rate, unsupported-claim rate, latency, and memory. A high mAP alone does not make the system safe.
4. Keep the work reproducible | Record model versions, prompts, thresholds, splits, random seeds, failed experiments, and Colab hardware. These notes become the README and interview story.
CORE TECH STACK
Environment | Google Colab GPU + Google Drive for persistent data and checkpoints
Language / Frameworks | Python, PyTorch, Ultralytics, Hugging Face Transformers
Perception models | YOLO-World baseline; YOLOE-26s-seg comparison; Grounding DINO optional
Vision-language model | Qwen3-VL-2B-Instruct for image understanding, structured reasoning, and evidence-linked reports
Data / labels | PPE images with person, hardhat, safety-vest boxes; person–PPE associations; compliance labels; frozen train/validation/test splits
Demo / hosting | Gradio on Hugging Face Spaces; GitHub repository with notebooks, experiment tables, dataset card, model card, and README
HOW TO USE THIS FILE
Tabs | Task Breakdown = the step-by-step checklist. Tools & Resources = official links. Glossary = plain-English definitions of CV, VLM, evaluation, and research terms.
Tracking | Update the Status dropdown after evidence is saved (not merely after code runs). The progress formulas below update automatically.
PROGRESS
Tasks done | 5
Total tasks | 46
% complete | 10.87%

## Task Breakdown
Phase | Step | Task | What to do / how (detailed) | Tools & Resources | Est. time | Status
Phase 0 — Setup & Foundations | 1 | Create and verify accounts | Verify Google, GitHub, and Hugging Face accounts. Record the GitHub repo and future Space URL in your notes; never store access tokens in notebooks. | GitHub / Hugging Face / Google | 30 min | Not started
Phase 0 — Setup & Foundations | 2 | Open Colab and enable GPU | Create the project notebook, enable a GPU runtime, mount Google Drive, and save Python, PyTorch, CUDA, GPU, and package versions. | Google Colab | 30 min | Not started
Phase 0 — Setup & Foundations | 3 | Finish Git repo setup | The repository exists and is connected. Commit the .gitignore, keep data/models/secrets out of Git, and confirm that main pushes successfully. | GitHub | 1 hr | Done
Phase 0 — Setup & Foundations | 4 | Python refresher | Be comfortable reading and editing functions, loops, lists, dictionaries, files, JSON, and basic pandas tables. | Python tutorial | 2–4 hrs | Not started
Phase 0 — Setup & Foundations | 5 | PyTorch refresher | Understand tensors, models, inference, GPU placement, no_grad/inference_mode, and why pretrained weights are reused. | PyTorch 60-Minute Blitz | 3–4 hrs | Not started
Phase 0 — Setup & Foundations | 6 | Learn core CV concepts | Understand detection, segmentation, bounding boxes, masks, confidence, IoU, NMS, precision, recall, and mAP. | Glossary / Ultralytics metrics | 2–3 hrs | Not started
Phase 0 — Setup & Foundations | 7 | Learn VLM concepts | Understand vision encoders, image tokens, multimodal prompting, visual grounding, structured outputs, hallucination, and evidence grounding. | Qwen3-VL / Transformers | 3–4 hrs | Not started
Phase 1 — Freeze detector baseline | 8 | Keep YOLO-World as the baseline | Preserve the completed YOLO-World approach as the detector-only baseline. Do not replace it or erase its outputs. | Ultralytics YOLO-World | 30 min | Done
Phase 1 — Freeze detector baseline | 9 | Install and load YOLO-World | Keep a clean Colab cell that installs a recorded Ultralytics version, loads the selected checkpoint, and reports the runtime environment. | Ultralytics | 1 hr | Done
Phase 1 — Freeze detector baseline | 10 | Run the first open-vocabulary detection | Run one reproducible example with an image and a class list; save boxes, class names, confidence scores, and the annotated image. | YOLO-World | 1–2 hrs | Done
Phase 1 — Freeze detector baseline | 11 | Visualise and test prompts | Compare several class-name and synonym prompt sets using the same image, model, image size, and confidence threshold. | Ultralytics / matplotlib | 2 hrs | Done
Phase 1 — Freeze detector baseline | 12 | Explain detector inputs and outputs | Write a short explanation of image input, class prompts, xyxy boxes, class IDs, confidence, threshold effects, and typical failure modes. | Project notes | 1–2 hrs | Not started
Phase 1 — Freeze detector baseline | 13 | Publish the baseline notebook | Save a clean 01_yoloworld_baseline.ipynb with deterministic inputs, environment versions, outputs, and a short limitations section. | Colab / GitHub | 2 hrs | Not started
Phase 2 — Run a VLM baseline | 14 | Choose the VLM | Use Qwen3-VL-2B-Instruct as the Colab starting point. Record its exact revision and licence; use quantisation only if the runtime requires it. | Qwen3-VL model card | 1 hr | Not started
Phase 2 — Run a VLM baseline | 15 | Install and load the VLM | Create 02_qwen3_vl_baseline.ipynb, load the processor and model, run one image-to-text request, and record GPU memory usage. | Transformers / Qwen3-VL | 2–3 hrs | Not started
Phase 2 — Run a VLM baseline | 16 | Test image description and VQA | Ask controlled PPE questions such as what equipment is visible, who appears non-compliant, and which evidence supports the answer. Save raw responses. | Qwen3-VL | 2–3 hrs | Not started
Phase 2 — Run a VLM baseline | 17 | Define a structured JSON output | Require person_id, PPE status, violations, evidence IDs, explanation, and uncertain. Validate every response against a fixed schema. | JSON Schema | 2–3 hrs | Not started
Phase 2 — Run a VLM baseline | 18 | Probe hallucination and uncertainty | Create clear, crowded, occluded, small-object, and no-PPE test cases. Record unsupported claims and whether the model admits uncertainty. | Project test images | 3 hrs | Not started
Phase 2 — Run a VLM baseline | 19 | Freeze the VLM-only baseline | Save the prompts, generation settings, structured-output validity, example successes, failures, latency, and memory before adding detector evidence. | Experiment table | 2 hrs | Not started
Phase 3 — Define problem & data | 20 | Freeze the research question | Use the question: does detector + explicit spatial rules + VLM reduce false-safe decisions and unsupported claims versus detector-only and VLM-only baselines? | Research protocol | 1 hr | Not started
Phase 3 — Define problem & data | 21 | Define PPE classes and rules | Start with person, hardhat, and safety vest. Define per-person rules and an uncertain state. Do not treat 'person wearing a helmet' as one ordinary object class. | PPE policy notes | 2 hrs | Not started
Phase 3 — Define problem & data | 22 | Select and licence the dataset | Choose a labelled PPE dataset or collect images. Record source, licence, privacy constraints, class definitions, and permitted redistribution. | Roboflow Universe / dataset card | 3–5 hrs | Not started
Phase 3 — Define problem & data | 23 | Create group-aware splits | Create train, validation, and frozen test splits by video, site, or capture session. Never place adjacent frames or duplicates in different splits. | Python / Google Drive | 2–4 hrs | Not started
Phase 3 — Define problem & data | 24 | Design the annotation schema | Store image ID, boxes/masks, classes, person–PPE associations, per-person compliance, violation type, evidence IDs, ambiguity, and reviewer notes. | Roboflow / JSON | 3–5 hrs | Not started
Phase 3 — Define problem & data | 25 | Audit annotations and duplicates | Check corrupt images, missing labels, invalid boxes, class imbalance, duplicate images, tiny objects, occlusion, and inconsistent safety labels. | Dataset audit notebook | 3–5 hrs | Not started
Phase 3 — Define problem & data | 26 | Write the dataset card | Document collection, licence, splits, classes, annotation rules, demographic or scene limitations, known biases, and prohibited uses. | GitHub Markdown | 2–3 hrs | Not started
Phase 4 — Build & evaluate hybrid system | 27 | Learn the complete metric set | Use mAP50-95 and per-class P/R for perception; association accuracy and macro-F1 for relations; false-safe rate for safety; schema validity and unsupported-claim rate for the VLM. | Ultralytics validation / Glossary | 3 hrs | Not started
Phase 4 — Build & evaluate hybrid system | 28 | Build the frozen ground-truth test set | Human-verify boxes, person–PPE relationships, compliance labels, and ambiguous cases. Do not use the test set for prompt or threshold selection. | Annotation tool | 4–8 hrs | Not started
Phase 4 — Build & evaluate hybrid system | 29 | Measure the detector-only baseline | Evaluate the saved YOLO-World baseline with fixed prompts and thresholds. Record metrics, runtime, memory, and error examples. | Ultralytics val / custom evaluator | 3–4 hrs | Not started
Phase 4 — Build & evaluate hybrid system | 30 | Measure the VLM-only baseline | Evaluate direct image-to-compliance answers without detector JSON. Record decision F1, false-safe rate, schema validity, unsupported claims, and latency. | Qwen3-VL evaluator | 3–4 hrs | Not started
Phase 4 — Build & evaluate hybrid system | 31 | Build person–PPE association rules | Associate hardhats with head regions and vests with torso regions using containment, overlap, centre distance, and explicit uncertainty for conflicts. | Python / geometry | 4–6 hrs | Not started
Phase 4 — Build & evaluate hybrid system | 32 | Build the grounded hybrid pipeline | Pass the original image or person crops, detector JSON, association results, and safety rules to the VLM. Require evidence IDs and reject malformed outputs. | YOLO-World + Qwen3-VL | 5–8 hrs | Not started
Phase 4 — Build & evaluate hybrid system | 33 | Run prompt and threshold ablations | Change one factor at a time: class wording, detector threshold, VLM prompt, crop strategy, and uncertainty instruction. Keep splits and models fixed. | Experiment protocol | 4–6 hrs | Not started
Phase 4 — Build & evaluate hybrid system | 34 | Compare a modern perception model | Compare YOLOE-26s-seg with YOLO-World on the same subset. Grounding DINO is optional if time remains; report accuracy-speed trade-offs. | YOLOE / Grounding DINO | 4–6 hrs | Not started
Phase 4 — Build & evaluate hybrid system | 35 | Fine-tune only if justified | Optional: fine-tune a small detector or use LoRA for the VLM only after zero-shot baselines expose a specific failure. Never train a foundation model from scratch. | Ultralytics / PEFT | 1 week | Not started
Phase 4 — Build & evaluate hybrid system | 36 | Record results and error analysis | Compare detector-only, VLM-only, rules-only, and hybrid systems. Report confidence intervals or bootstrap ranges, false-safe cases, hallucinations, and qualitative examples. | Results table / error gallery | 4–6 hrs | Not started
Phase 5 — Build the demo | 37 | Learn Gradio basics | Understand image upload, policy/question input, annotated-image output, table/JSON output, examples, errors, and queue behaviour. | Gradio | 1–2 hrs | Not started
Phase 5 — Build the demo | 38 | Build the grounded PPE app | Input an image and selected PPE rules. Output boxes/masks, a per-person compliance table, violations, evidence IDs, explanations, and uncertainty. | Gradio | 4–6 hrs | Not started
Phase 5 — Build the demo | 39 | Add traceable evidence and safeguards | Let users match each conclusion to a detection. Show thresholds, model versions, an uncertainty state, and a warning that this is a research prototype, not a safety guarantee. | Gradio / app config | 3 hrs | Not started
Phase 5 — Build the demo | 40 | Polish and test the interface | Add 3–5 representative examples, loading/error states, readable labels, clear limitations, and tests for empty detections and malformed VLM output. | Gradio | 3–4 hrs | Not started
Phase 5 — Build the demo | 41 | Deploy to Hugging Face Spaces | Deploy the lightest reliable configuration. Record CPU/GPU limitations; use a GPU or on-demand/API VLM if the free CPU Space cannot host the full pipeline. | Hugging Face Spaces | 3–5 hrs | Not started
Phase 6 — Document & ship | 42 | Write the research README | Explain the problem, research question, architecture, dataset, baselines, metrics, ablations, results, screenshots, demo, reproduction steps, and honest limitations. | GitHub Markdown | 4–6 hrs | Not started
Phase 6 — Document & ship | 43 | Add reproducibility files | Add requirements or environment lock, configs, prompts, evaluation settings, random seeds, .gitignore, licence, and instructions for obtaining data and weights. | GitHub | 2–4 hrs | Not started
Phase 6 — Document & ship | 44 | Add dataset/model cards and safety limits | Document licences, intended use, excluded use, bias, hallucination risk, false-safe risk, privacy, and the fact that the system is not suitable for automated enforcement. | Hugging Face / GitHub | 3 hrs | Not started
Phase 6 — Document & ship | 45 | Push notebooks, code, and fixed results | Push clean notebooks, app code, configs, metrics tables, and a small error gallery. Do not commit datasets, secrets, caches, large weights, or Colab runtime files. | GitHub | 2 hrs | Not started
Phase 6 — Document & ship | 46 | Publish and present the project | Share a concise post or report covering the research question, strongest result, key failure, responsible-use limits, live demo, and repository. | LinkedIn / blog / portfolio | 2–3 hrs | Not started

## Tools & Resources
Tool / Resource | What it's for | Official source
Google Colab | GPU notebooks for all project experiments. | https://colab.research.google.com
PyTorch 60-Minute Blitz | Framework refresher covering tensors, neural networks, training, and inference. | https://pytorch.org/tutorials/beginner/deep_learning_60min_blitz.html
Ultralytics YOLO-World | Existing open-vocabulary detection baseline. | https://docs.ultralytics.com/models/yolo-world/
Ultralytics YOLOE | Modern text/visual-prompt open-vocabulary detection and segmentation comparison. | https://docs.ultralytics.com/models/yoloe/
Ultralytics validation | Detection metrics and validation interface. | https://docs.ultralytics.com/modes/val/
Qwen3-VL | Official repository for the multimodal vision-language model family. | https://github.com/QwenLM/Qwen3-VL
Qwen3-VL-2B-Instruct | Lightweight VLM checkpoint selected for the Colab baseline. | https://huggingface.co/Qwen/Qwen3-VL-2B-Instruct
Hugging Face Transformers | Model loading, processors, generation, quantisation, and evaluation utilities. | https://huggingface.co/docs/transformers
Grounding DINO | Optional higher-cost open-set detector comparison. | https://github.com/IDEA-Research/GroundingDINO
Roboflow Universe | Candidate labelled PPE datasets and annotation tooling. | https://universe.roboflow.com
Gradio | Build the interactive evidence-linked PPE demo. | https://www.gradio.app
Hugging Face Spaces | Host the demo and document CPU/GPU constraints. | https://huggingface.co/docs/hub/spaces-overview
GitHub | Version notebooks, code, configs, fixed results, cards, and README. | https://github.com/Limeng-svg/Project_Detection
JSON Schema | Validate structured VLM outputs instead of relying on free-form text. | https://json-schema.org

## Glossary
Term | Plain-English meaning
Object detection | Finding objects in an image and returning a labelled box around each one.
Instance segmentation | Finding each object and predicting its exact pixel-level mask, not only a rectangle.
Bounding box | The rectangle around an object, often stored as x-min, y-min, x-max, and y-max.
Confidence score | The detector's score for a prediction. It is useful for ranking and thresholding, but is not automatically a calibrated probability.
Open-vocabulary detection | Detecting categories specified by text or visual prompts instead of relying only on a fixed training label list.
Vision-language model (VLM) | A multimodal model that receives images and text and generates text or structured responses about the visual content.
Vision encoder | The neural-network component that converts image regions into numerical visual features or image tokens.
Image token | A numerical representation of an image patch or visual feature that can be processed alongside text tokens.
Visual grounding | Linking a word, phrase, or model conclusion to a specific region, box, point, or mask in the image.
Prompt | The text instruction or category list given to a detector or VLM.
Structured output | A response constrained to a fixed machine-readable format such as JSON with required fields.
JSON Schema | A formal definition of allowed JSON fields and value types, used to validate model responses.
Hallucination | A confident model statement that is unsupported by the image, detector evidence, or supplied rules.
Evidence grounding | Requiring every safety conclusion to cite real detection IDs, regions, relationships, or other visible evidence.
Uncertainty state | An explicit outcome used when the evidence is occluded, too small, conflicting, or otherwise insufficient for a reliable decision.
Person–PPE association | Determining which hardhat or vest belongs to which detected person in a multi-person scene.
Compliance rule | A clear rule that maps person–PPE evidence to compliant, non-compliant, or uncertain.
False-safe rate | The fraction of truly unsafe or non-compliant cases incorrectly reported as safe. This is a primary risk metric for the project.
Ground truth | Human-verified boxes, relationships, and conclusions used to evaluate model predictions.
IoU (Intersection over Union) | The overlap between a predicted region and the ground-truth region, from 0 to 1.
Precision | Of all reported positives, the fraction that were correct.
Recall | Of all real positives, the fraction the system found.
Macro-F1 | The average F1 score across classes, giving each class equal weight even when class frequencies differ.
mAP50-95 | Detection average precision averaged over IoU thresholds from 0.50 to 0.95.
Validation set | A held-out split used to choose prompts, thresholds, and settings.
Test set | A frozen held-out split used only after design choices are complete, to estimate final performance.
Data leakage | When related or duplicated samples appear across splits and make evaluation look better than real-world generalisation.
Baseline | A fixed starting system that later methods must be compared against under the same conditions.
Ablation study | A controlled experiment that changes or removes one component at a time to measure its contribution.
Fine-tuning | Updating a pretrained model on task-specific data rather than training from scratch.
LoRA / PEFT | Parameter-efficient methods that train a small number of additional parameters instead of updating the full large model.
Inference | Running a trained model on new data to produce predictions or generated answers.
Latency | The time from receiving an input to producing an output.
Reproducibility | The ability to rerun the same experiment using recorded data splits, code, model versions, prompts, settings, and seeds.
Dataset card | A document describing data source, licence, collection, annotations, splits, bias, privacy, limitations, and intended use.
Model card | A document describing a model or system's intended use, evaluation, limitations, risks, licences, and responsible-use guidance.
Gradio | A Python library used to build the project's interactive web interface.
README | The repository front page explaining the problem, system, results, demo, reproduction, and limitations.